## Exam response timeline
Illustrative template from InsureAI Wire (insureaiwire.com). The example row is illustrative, not a real company's data. This is information, not legal advice: calibrate to your own situation and confirm with counsel.
Phase | Planning cue | Key action | Owner | Deliverable | Deadline
Exam notice received | Immediately | Log receipt, acknowledge to regulator, open exam file | Compliance officer | Acknowledgment letter + internal exam file opened | As stated in the notice
Kickoff call | After initial review | Confirm scope, document requests, timeline, contacts | Compliance + legal | Kickoff minutes + confirmed document list | As agreed with the department
Document collection | After scope is confirmed | Pull AIS Program, inventories, validation records, vendor contracts | Compliance + IT + actuarial | Document index with Bates numbers | Per exam schedule
Internal review | Before submission | Gap check against the request and applicable authorities | Compliance + legal | Gap list with owners and remediation dates | Before submission
Submission | By the department's deadline | Deliver documents, log transmittal, confirm receipt | Compliance officer | Transmittal letter + delivery confirmation | Per exam schedule
On-site / interview | If requested | Prepare witnesses, run mock interviews, document Q&A | Compliance + business leads | Interview prep memo + Q&A log | Before the interview
Findings response | After findings issue | Draft response and corrective action plan if needed | Legal + compliance + CRO | Response letter + CAP | Per regulator deadline

## Documentation checklist
Illustrative template from InsureAI Wire (insureaiwire.com). The example row is illustrative, not a real company's data. This is information, not legal advice: calibrate to your own situation and confirm with counsel.
# | Documentation item | What the examiner sees | What counts as solid | Gap sign | Owner
1 | AIS Program document | A written AI Systems Program with adoption date, review frequency, and board approval | Dated minutes showing board or committee adoption; annual review entries | Undated document, or one with no review history | CRO / Chief Compliance Officer
2 | AI inventory (feeds Exhibit A) | A list of every AI system, with operational area, owner, vendor flag, and last validation date | Each entry has a named owner and a validation date inside your stated revalidation interval | Systems listed without owners, or validation dates with no interval to measure them against | Chief Actuary / Model Risk
3 | High-risk system documentation (Exhibit C) | Per model: name and version, type, implementation date, built or bought and by which vendor, risk classification, known risks and limitations, whether it automates or only supports, how it was validated and is monitored, last test date, and any regulatory action taken over it | Dated validation reports, bias and unfair-discrimination test results, a last-testing date that is not years old | Validation reports with no dates, or bias testing that says "N/A" | Model Risk / Chief Actuary
4 | Data lineage (Exhibit D) | Not a free-text lineage narrative: a fixed list of data-element categories: age, gender, ethnicity/race, geocoding, geo-demographics, education, income, criminal convictions, facial analysis and the rest: where you mark which ones feed your models and whether each came from inside the company or from a named third party | A defensible answer for every category you checked, and a data dictionary behind it | Data sources listed as "various internal systems" with no further detail | Data Governance
5 | Vendor contracts and due diligence | Contracts with audit rights, model documentation clauses, monitoring provisions | Signed contracts with specific AI audit clauses; due-diligence files with dates | Contracts signed before AI was added, with no amendment covering AI | Procurement / Legal
6 | Consumer notice and complaint log | Records of AI-related consumer disclosures and any complaints or appeals | Notice templates, mailing or portal logs, complaint register with AI flag | No AI-specific complaint category, or complaints handled in general queue only | Customer Service / Compliance
7 | Governance meeting minutes | Minutes from AI governance committee or risk committee meetings | Dated minutes with AI agenda items, attendance, and action items | Minutes with no AI items, or attendance that does not include the model owner | CRO / Corporate Secretary
8 | Incident and override log | Records of AI incidents, near-misses, and human overrides | Dated entries with root-cause analysis and remediation | Empty log, or entries that say "no issues found" without detail | Model Risk / IT

## Gap record
Illustrative template from InsureAI Wire (insureaiwire.com). The example row is illustrative, not a real company's data. This is information, not legal advice: calibrate to your own situation and confirm with counsel.
Gap # | Exam request or finding | What we could not produce | Why | Interim control | Owner | Due date
G-01 | Produce validation records for the claims triage model | No validation performed since 2025 rebuild | Model rebuilt by vendor without a re-validation clause in the contract | Manual review of all triage decisions until validation completed | Chief Actuary | 2026-Q3
G-02 | Show proxy-discrimination screening for geo score | No proxy screen documented | Geo score added in 2024, before proxy screening was part of the standard intake | Run the disparate-impact test now; document methodology and results | Model Risk | 2026-Q4
3
4
5
6
7
8
9
10
11
12